## Sheet2
MCI Project Weekly Time Sheet
Team | KM5a | Student ID | a1786571 |  |  | Week starting: | 3
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 17/3/2025 | 9:00 | 14:00 | 5 | Study quantum logic gates, deepen knowledge on other basic concept | Have a more complete understanding of every concept so I could helps more on game design and coding part when we start to allocate task | Understand all concept and ready to translate into game design and code
Wednesday | 19/3/2025 | 10:00 | 17:00 | 7 | Ready for meeting, discuss about the main concept and game mechanism, allocate all the tasks to everyone | Start doing pratical task and progressing on the project | Got my part of what I should do in the coding part
Thursday | 20/3/2025 | 9:00 | 17:00 | 8 | Clone the project from github and learn all the code and how the project is like now from what Hermanto did | Understand the code so I can start implementation smoothly when Hermanto finish his part and I can continue on that | Ready to implement the ability upgrades (quantum gates)
Friday | 21/3/2025 | 11:00 | 18:00 | 7 | Discuss the project after lecture, prepare ppt and script for pitch presentation, plan on how to integrate the upgrades with quantum gates concept | Confirm we all on track and progess on the project and be ready for the pitch recording | Wait Hermanto to finish the grid system so me and Chelsea can implement the upgrades(quantum gates) and connection(quantum entanglement)
Saturday | 22/3/2025 | 11:00 | 17:00 | 6 | Prepare ppt and script for pitch presentation | Pitch present for our project | Practice the script with the ppt
Sunday | 23/3/2025 | 17:00 | 19:00 | 2 | Discuss everyone's part of the presentation and check if we miss anything | Ready for the video recording | Record video, edit video and prepare for qna
|  |  | Total | 35