## Sheet2
MCI Project Weekly Time Sheet
Team | KM5a | Student ID | a1894037 |  |  | Week starting: | 4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2024-03-01 | 17:00 | 22:00 | 5 | Finalized pitch slides and start recording a first draft. | Need to combine our pitch presentation and showcase to the client on Wednesday, also need to use as a sample recording for the rest of the team to refer to (unifom formatting and so on) | Finished and uploaded to google drive and gathering teammates feedback.
Tuesday | 2025-03-25 | 14:00 | 17:00 | 3 | Start to take a look around our unity project. | Need to get familiar with our project, codes, scenes etc. | Wait until finished the pitch presentation to start coding.
Wednesday | 2026-03-01 | 10:00 | 14:00 | 4 | Prepared for client meeting, reviewed what I did last week and this week so far, and listed questions should be asked during the meeting. Had the meeting. Showcased our pitch presentation and received feedback. | Since it’s the client who will grade our presentation and also review our project it’s important to know his perspective. | Gathered what to improve for the pitch and prepare to discuss during FRIDAY'S meeting.
Thursday | 2027-03-01 | 17:00 | 20:30 | 3.5 | Start initial developing of entanglement feature. | Entanglement is a key feature of this quantum computing educational game. | Continued on Friday.
Friday | 2028-03-01 | 11:00 | 15:30 | 4.5 | Attended lecture, had group discussing afterwards. | Discussed our pitch presentation, making sure everyone knows what they should do (re-recording, editing, etc.) Assigned business case part. | Aim to submit on time.
Saturday | 2029-03-01 | 11:30 | 16:40 | 5 | Continue entanglement feature | Core quantum computing feature of the game. | Got the majority done, need some refactoring.
Sunday | 1930-03-01 | 12:00 | 17:00 | 5 | Continue entanglement feature. Drafting business case assigned part. | Need a data structure for this feature, researching. | Cannot finish this week, need to cont next week.
|  |  | Total | 30