## Sheet2
MCI Project Weekly Time Sheet
Team | KM5a | Student ID | a1918614 |  |  | Week starting: | 2025-03-17
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-03-17 | 18:00 | 21:00
Tuesday | 2025-03-18 | 17:00 | 12:00 | 7 | Generating ideas on how to better integrate more concepts into the game. | Some additional ideas were left out. We brainstormed and discussed them in the Discord group to decide how to implement the remaining concepts | The group collaboratively shared ideas on how to incorporate the multi-qubit concept into the game
Wednesday | 2025-03-19
Thursday | 2025-03-20
Friday | 2025-03-21 | 11:00 | 23:00 | 12 | We held a class and group meeting, followed by individual brainstorming. Additionally, we discussed the game’s development progress. | This helped maintain focus on the project’s core tasks and the development of the game. | We discussed both the front-end and back-end of the game and explored ways to improve their efficiency.
Saturday | 2025-03-22 | 4:00 | 12:00 | 8 | While developing the game, I reviewed the work from previous weeks. I opened the project, ran it, and experimented with changing some parts to better understand how everything works. | Revisiting and modifying previous work helps reinforce our understanding of the games structure, enabling us to make more effective improvements | Worked on developing the game by adding new features and refining existing ones
|  |  | Total | 27